# Simplified tender procedures

- INFORMATION ON SUBMISSION OF THE TENDERS

| - Publication reference: | 07 - 2026 |
| --- | --- |
| - Project Title: | One voice for LGAs in Albania, phase 2 |
| - Subject of the contract: | Social Services Expert to Support NAMA’s Forum on Social Services |
| - Contracting Authority: | NALAS Network of Associations of Local Authorities of South-East Europe, Branch in Albania |
| - Maximum Budget: | Maximum budget available EUR 9,500.00 (nine thousand five hundred euro) VAT excluded |
| - Deadline for application: | 20.02.2026, at 16:00 |

- Contract description

NALAS promotes the process of decentralisation in partnership with its member LGAs and in cooperation with central governments and international organisations, considering local self-government as a key issue in the current process of transition affecting the various countries in South-East Europe. NALAS initiates and carries out regional initiatives for its members and helps LGAs to become viable representatives of local authorities vis-à-vis their central government.

With the support of the Swiss Development Cooperation (SDC), NALAS is providing strategic, institutional, and operational support to the National Association of Municipalities of Albania (NAMA). This initiative is part of a broader effort to strengthen NAMA’s capacity to effectively represent the collective interests of all Albanian municipalities and to play a more active and influential role in national and international policy processes.

Municipalities in Albania are responsible for an expanding range of social services, including child protection, social care, and emergency response, often operating under fragmented regulatory frameworks, limited professional supervision mechanisms, and inconsistent service standards.

To address these challenges, NAMA has established the Forum on Social Services as a technical platform bringing together municipal practitioners, social service professionals, and institutional stakeholders. The Forum aims to strengthen professional standards, support harmonization of practices, and promote evidence-based dialogue with central institutions, particularly in areas such as professional supervision, emergency case management, and standardized service provision.

Within this framework, and with the support of SDC, NALAS will engage a Social Services Expert to provide technical expertise and capacity building support to NAMA’s Forum on Social Services. The assignment will contribute to improving the quality, consistency, and professionalism of municipal social services, while strengthening NAMA’s role as a policy-competent and technically credible association.

The objective of the assignment is to strengthen the technical capacity and outputs of NAMA’s Forum on Social Services by supporting the development of key methodological and guidance documents and by delivering targeted peer exchange and training activities for municipalities.

Specifically, the assignment aims to:

- Support the development of professional, standardized, and practice-oriented guidance for municipal social services.

- Strengthen municipal capacities in managing emergency cases and delivering standardized social services.

- Facilitate peer learning and structured technical dialogue among municipalities and relevant stakeholders.

The scope of work includes the following components:

Technical Deliverables

- Development of Guidelines on Professional Supervision in Social Services

- Review of the legal framework, EU practices, and national standards on professional supervision

- Drafting of guidelines on professional supervision in social services

- Technical consultations and integration of feedback (workshop / focus group)

- Finalization and submission of the guidelines

- Development of a Unified Methodology / Protocol for Emergency Cases and Domestic Violence

- Review of legal framework, existing protocols, and EU good practices

- Drafting of the unified methodology / protocol

- Inter-institutional consultations and coordination meetings

- Workshop / focus group for validation

- Revision, validation, and finalisation

Capacity Building Deliverables

- Peer Exchange / Training on Managing Emergency Cases (Social Services Forum Meeting 1)

- Preparation of training agenda, methodology, and materials

- Delivery of peer exchange / training session(s)

- Reporting, documentation of results, and recommendations

- Training on Standardized Social Service Provision (Social Services Forum Meeting 2)

- Review of standardized social service frameworks and policies

- Development and adaptation of training modules and materials

- Delivery of training session(s)

- Training report and follow-up recommendations

Coordination and Demand-Driven Support

- Provide technical input and advisory support to NAMA for Social Services Forum discussions, as requested.

- Support NAMA and NALAS in preparing background materials, agendas, and follow-up actions related to social services.

- Ensure alignment of technical outputs with national reforms, EU standards, and municipal practice.

The duration of the contract is expected to be up to 40 working days, starting from February 2026.

- Selection Criteria

# The expert must meet the following minimum qualifications:

Qualifications and skills:

- University degree in social work, social policy, psychology, public administration, law, or a related field.

- Excellent analytical and advisory skills.

- Fluency in English (oral and written).

# General Work Experience

- At least 10 years of proven relevant work experience.

# Specific Work Experience

- At least 8 years of professional experience in social services, child protection, or social care systems at municipal or national levels or in specialized organizations.

- Demonstrated experience in developing guidelines, protocols, or methodologies in the field of social services.

- Demonstrated experience in designing and delivering capacity building events, workshops or peer learning on social services with municipalities or public institutions.

- Familiarity with EU social services standards and Albanian social protection frameworks is a strong asset.

- Award criteria

# The best price-quality ratio established by weighing technical quality against price on an 80/20 basis.

- Application procedure

# This call is open on equal terms to both companies and individuals.
If the applicant is a company, it must submit all documents related to the proposed key expert, as specified under paragraph “a) Technical Offer.” The designated key expert must be actively involved throughout the entire duration of the contract. Replacement of the key expert will be permitted only in exceptional circumstances and must be approved in writing by the Contracting Authority.

# Offers, all correspondence and documents related to the tender exchanged by the tenderer and the contracting authority must be written in English.

# The tender must comprise a technical offer and a financial offer, which must be submitted in separate envelopes or through specific electronic post mail messages.

- Technical offer

# The applicant must submit a Technical Offer comprising the following documents:

- Cover Letter: Explaining the expert’s suitability for the assignment, as specified in this Terms of Reference (ToR);

- Detailed CV: Clearly demonstrating how the expert meets the eligibility and qualification criteria outlined in Article 8;

- Identification Form: Completed and signed.

In case of individual expert, the Identification form shall be completed as a natural person.

- Financial offer

# The financial offer must be presented as an amount in Euro, VAT excluded and must be submitted using the template Financial Offer as given by the Contracting Authority in which the applicants will specify the daily fee they offer.

# Expert must be independent and free from conflicts of interest in the responsibilities they take on.

- Submission of tenders

Tenders may be submitted using the double envelope system, i.e. in an outer parcel or envelope containing two separate, sealed envelopes, one bearing the words ‘Envelope A — Technical offer’ and the other ‘Envelope B — Financial offer’. All parts of the tender other than the Financial Offer template must be submitted in Envelope A.

Alternatively, tenders may be submitted using two specific electronic post mails, specifying ‘Envelope A — Technical offer’ and the other ‘Envelope B — Financial offer’.

The outer envelope should provide the following information:

a) the address for submitting tenders indicated above.

b) the reference code for the tender procedure.

c) the words ‘Not to be opened before the tender-opening session’.

d) the name of the tenderer.

Tenders must be sent to the contracting authority before 20.02.2026, at 16:00. They must include the requested documents in clause 10 above and be sent:

- by post or by courier service, in which case the evidence shall be constituted by the postmark or the date of the deposit slip, to:

NALAS Branch in Albania

Address: “Donika Kastrioti” Street, Tekno-Project bldg.

4th floor, Apt. 3/1, Tirana, Albania

- OR hand delivered by the participant in person or by an agent directly to the premises of the contracting authority in return for a signed and dated receipt, in which case the evidence shall be constituted by this acknowledgement of receipt, to:

NALAS Branch in Albania

Address: “Donika Kastrioti” Street, Tekno-Project bldg.

4th floor, Apt. 3/1, Tirana, Albania

- Applications can be submitted also by email at the following email address: info@nalas.eu, by specifying in the subject the title of the expertise they are applying for.

- Evaluation of tenders

The tenders will be evaluated on the basis of conformity with the requirements of this tender dossier and procedure. A technical and financial evaluation will be performed by the evaluation committee on the technical and financial admissibility of tenders.

# Evaluation Grid for the technical evaluation is specified as follows:

|  | # Maximum |
| --- | --- |
| # Qualifications and skills | # 30 |
| # General Work Experience | # 30 |
| # Specific Work Experience | # 40 |
| # Overall total score | # 100 |

# Only tenders scoring at least 75 points in the technical evaluation will proceed to financial evaluation.

- Notification of award

The contracting authority will inform all tenderers simultaneously and individually of the award decision.

- Other

For more information the applicants may consult the Terms of Reference attached to this tender procedure.